## Sheet1
Gantt Chart API E-Commerce
Taks |  | June 2022
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Planning | bar: June 2022 2; June 2022 6
api customers | register | bar: June 2022 3
validation email | bar: June 2022 5
login | bar: June 2022 3
logout | bar: June 2022 3
forget-password | bar: June 2022 6
get profile | bar: June 2022 7
edit profile | bar: June 2022 7
change profile picture | bar: June 2022 7
api merchants | register | bar: June 2022 8
validation email | bar: June 2022 8
login | bar: June 2022 8
logout | bar: June 2022 8
forget-password | bar: June 2022 9
get detail merchant | bar: June 2022 9
edit profile merchant | bar: June 2022 9
change profile picture | bar: June 2022 9 to June 2022 10
get products merchants | bar: June 2022 10
api products | add products | bar: June 2022 10
edit products | bar: June 2022 10
get all products | bar: June 2022 13
get products detail | bar: June 2022 13
delete products | bar: June 2022 13
api carts | add products to carts | bar: June 2022 13 to June 2022 14
get products in carts | bar: June 2022 14
edit products in carts | bar: June 2022 14
delete products in carts | bar: June 2022 14
api orders | create orders | bar: June 2022 15
email confirm | bar: June 2022 15
email to user result confirm | bar: June 2022 15 to June 2022 16
Create Admin Monitoring | bar: June 2022 16
Api Documentation | bar: June 2022 17

## Sheet2
Task | Start Date | End Date | Duration
Planning | 2022-07-02 | 2022-07-03 | 1
api register customers | 2022-07-03 | 2022-07-03 | 0
validation email customer | 2022-07-03 | 2022-07-03 | 0
login customer | 2022-07-03 | 2022-07-03 | 0
logout customer | 2022-07-03 | 2022-07-03 | 0
forgot-password customer | 2022-07-06 | 2022-07-06 | 0
edit profile customers | 2022-07-06 | 2022-07-06 | 0
change profile picture customer | 2022-07-06 | 2022-07-06 | 0
register merchant | 2022-07-07 | 2022-07-07 | 0
validation email merchant | 2022-07-07 | 2022-07-07 | 0
login merchant | 2022-07-07 | 2022-07-07 | 0
logout merchant | 2022-07-07 | 2022-07-07 | 0
forgot-password merchant | 2022-07-08 | 2022-07-08 | 0
edit profile merchant | 2022-07-08 | 2022-07-08 | 0
edit picture merchat | 2022-07-08 | 2022-07-08 | 0
add product | 2022-07-09 | 2022-07-09 | 0
edit product | 2022-07-09 | 2022-07-09 | 0
detail product | 2022-07-09 | 2022-07-09 | 0
delete product | 2022-07-09 | 2022-07-10 | 1
search merchant by produk name | 2022-07-10 | 2022-07-10 | 0
detail merchant | 2022-07-10 | 2022-07-10 | 0
add product to cart | 2022-07-10 | 2022-07-13 | 3
get product from cart | 2022-07-13 | 2022-07-13 | 0
edit product in cart | 2022-07-13 | 2022-07-13 | 0
delete product in cart | 2022-07-13 | 2022-07-13 | 0
orders | 2022-07-14 | 2022-07-14 | 0
email confirm order | 2022-07-14 | 2022-07-14 | 0
cms admin | 2022-07-15 | 2022-07-15 | 0
api docs | 2022-07-15 | 2022-07-15 | 0