## main
Gantt Chart API E-Commerce
Taks |  | June 2022
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Planning | bar: June 2022 2; June 2022 6
api customers | register | bar: June 2022 3
validation email | bar: June 2022 5
login | bar: June 2022 3
logout | bar: June 2022 3
forget-password | bar: June 2022 6
get profile | bar: June 2022 7
edit profile | bar: June 2022 7
change profile picture | bar: June 2022 7
api merchants | register | bar: June 2022 8
validation email | bar: June 2022 8
login | bar: June 2022 8
logout | bar: June 2022 8
forget-password | bar: June 2022 9
get detail merchant | bar: June 2022 9
edit profile merchant | bar: June 2022 9
change profile picture | bar: June 2022 9 to June 2022 10
get products merchants | bar: June 2022 10
get merchants by products name | bar: June 2022 10
api products | add products | bar: June 2022 10
edit products | bar: June 2022 10
get all products | bar: June 2022 13
get products detail | bar: June 2022 13
delete products | bar: June 2022 13
api carts | add products to carts | bar: June 2022 13 to June 2022 14
get products in carts | bar: June 2022 14
edit products in carts | bar: June 2022 14
delete products in carts | bar: June 2022 14
api orders | create orders | bar: June 2022 15
email confirm | bar: June 2022 15
email to user result confirm | bar: June 2022 15 to June 2022 16
Create Admin Monitoring | bar: June 2022 16
Api Documentation | bar: June 2022 17

## test
Taks |  | June 2022 | [15 empty] | Duration
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Planning | bar: June 2022 2; June 2022 6
api customers | register | bar: June 2022 3
validation email | bar: June 2022 5
login | bar: June 2022 3
logout | bar: June 2022 3
forget-password | bar: June 2022 6
| get profile | [16 empty] | jam 08.00-11.25 (7) | bar: June 2022 7
| edit profile | [16 empty] | jam 08.00-11.25 (7) | bar: June 2022 7
| change profile picture | [16 empty] | jam 08.00-11.25 (7) | bar: June 2022 7
api merchants | register | [17 empty] | jam 11.25 - 14.00 (7) | bar: June 2022 8
| validation email | [17 empty] | jam 11.25 - 14.00 (7) | bar: June 2022 8
| login | [17 empty] | jam 11.25 - 14.00 (7) | bar: June 2022 8
| logout | [17 empty] | jam 11.25 - 14.00 (7) | bar: June 2022 8
| forget-password | [18 empty] | jam 11.25 - 14.00 (7) | bar: June 2022 9
| get detail merchant | [18 empty] | jam 14.00 - 16.45 (7) | bar: June 2022 9
| edit profile merchant | [18 empty] | jam 14.00 - 16.45 (7) | bar: June 2022 9
| change profile picture | [18 empty] | jam 14.00 - 16.45 (7) | bar: June 2022 9 to June 2022 10
get products merchants | bar: June 2022 10
edit status merchant
get merchats by product name
api products | add products | bar: June 2022 10
edit products | bar: June 2022 10
get all products | bar: June 2022 13
get products detail | bar: June 2022 13
delete products | bar: June 2022 13
api carts | add products to carts | bar: June 2022 13 to June 2022 14
get products in carts | bar: June 2022 14
edit products in carts | bar: June 2022 14
delete products in carts | bar: June 2022 14
api orders | create orders | bar: June 2022 15
email confirm | bar: June 2022 15
email to user result confirm | bar: June 2022 15 to June 2022 16
Create Admin Monitoring | bar: June 2022 16
Api Documentation | bar: June 2022 17

## dummy
Taks |  | June 2022 | [15 empty] | Duration
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Planning | bar: June 2022 6
api customers | register | bar: June 2022 3
validation email | bar: June 2022 5
login | bar: June 2022 3
logout | bar: June 2022 3
forget-password | bar: June 2022 6
| get profile | [16 empty] | jam 08.00-11.25 (7)
| edit profile | [16 empty] | jam 08.00-11.25 (7)
| change profile picture | [16 empty] | jam 08.00-11.25 (7)
api merchants | register | [16 empty] | jam 11.25 - 14.00 (7)
| validation email | [16 empty] | jam 11.25 - 14.00 (7)
| login | [16 empty] | jam 11.25 - 14.00 (7)
| logout | [16 empty] | jam 11.25 - 14.00 (7)
| forget-password | [16 empty] | jam 11.25 - 14.00 (7)
| get detail merchant | [16 empty] | jam 14.00 - 16.45 (7)
| edit profile merchant | [16 empty] | jam 14.00 - 16.45 (7)
| change profile picture | [16 empty] | jam 14.00 - 16.45 (7)
| edit status merchant | [16 empty] | jam 14.00 - 16.45 (7)
| get merchant by product name | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| get products merchants | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
api products | add products | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| delete product image | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| add product image | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| edit status product | [16 empty] | jam 14:05 - 15:00 (8) | bar: June 2022 8
| edit products | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| get all products | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| get products detail | [16 empty] | jam 08.00 - 13.10 (8) | bar: June 2022 8
| delete products | [16 empty] | jam 14:05 - 15:00 (8) | bar: June 2022 8
api carts | add products to carts
get products in carts
edit products in carts
delete products in carts
api orders | create orders
email confirm
email to user result confirm
Create Admin Monitoring
Api Documentation