## Sheet1
Gantt Chart API E-Commerce
Taks |  | June 2022
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Planning | bar: June 2022 2 to June 2022 3
ApI Customer Auth: | Register | bar: June 2022 3
Validation Email | bar: June 2022 3
Login | bar: June 2022 3 to June 2022 4
Forgot-Password | bar: June 2022 4
Api User Profile | Edit Profile | bar: June 2022 4
Add Profile Picture | bar: June 2022 4 to June 2022 5
Api Merchant | Search Merchant | bar: June 2022 5
Detail Merchant | bar: June 2022 5
Api Products | Detail Product | bar: June 2022 5
Add Product | bar: June 2022 5 to June 2022 6
Edit Product | bar: June 2022 6
Delete Products | bar: June 2022 6
Api Carts | Get carts | bar: June 2022 6
Add Product to carts | bar: June 2022 7
Edit Product in carts | bar: June 2022 7
Delete Products in carts | bar: June 2022 7
Api Orders | Create orders | bar: June 2022 8
Email Confirm order | bar: June 2022 8
Api Auth Merchant | register | bar: June 2022 8
Validation Email | bar: June 2022 8
Approve Email to admin | bar: June 2022 9
Login | bar: June 2022 9
Forgot-Password | bar: June 2022 9
CMS Admin untuk montoring | bar: June 2022 9 to June 2022 10
Pembuatan API docs | bar: June 2022 10